## Sheet1
Barnstable County Dredge Department Schedule For 2021 - 2022
Project Order | TOWN | Dredge Site | Est. Vol. | Receiving | Pipeline | Booster | TOY's | Planned Start Date | Start Date | End Date | Pre-Dredge Volume | Post-Dredge Volume
|  |  | (CY) | Site | (LF) | (Y/N)
| Dredge Cod Fish II |  |  | Dredge Cod Fish II |  |  | Dredge Cod Fish II |  |  | Dredge Cod Fish II
1 | Mashpee | Inner Channel | 4000 | Poppenessett Spit | 3000 | N | CLOSE DTOY 1/14 | 2021-09-27 | 2021-10-12 | 2021-10-16 | 2117 | 1610
2 |  | 1916 Channel | 5000 | Poppenessett Spit | 4000 | N | CLOSE DTOY 1/14 | 2021-10-05 | 2021-10-18 | 2021-10-29 | 3688 | 3454
3 | Truro | Pamet Harbor/Inlet & Approach Ch | 7000 | Corn Hill Beach | 1550 | N | CLOSE DTOY 1/31 | 2021-10-14 | 2021-12-09 | 2021-12-30 | 2428 | 1127
4 |  | Pamet Harbor Mooring Basin | 13000 | Corn Hill Beach | 3000 | N | CLOSE DTOY 1/31 | 2021-10-25 | 2021-12-09 | 2021-12-30 | 3069 | 2172
5 | Provincetown | MacMillan Pier Central Fairway | 5000 | MacMillan Pier Parking Lot/Upland Disposal | 2500 | N | CLOSE DTOY 1/31 | 2021-11-10
6 | Dennis | Sesuit Harbor | 15000 | Cold Storage Beach | 1600 | N | CLOSE DTOY 1/31 | 2021-11-20 | 2022-01-12 | 2022-01-31 | 13278 | 16303
7 | Barnstable | Barnstable Harbor Outer Entrance | 4000 | Sandy Neck Cottage/ Millway | 8500 | Y | CLOSE DTOY 1/31 | 2021-12-11
8 | Falmouth | Megansett | 3000 | Megansett Beach | 1500 | N | CLOSE DTOY 3/31 | 2021-12-27
9 |  | Inner Harbor | 1500 | Surf Beach | 3800 | N | CLOSE DTOY 1/14 | 2021-01-10 |  |  | 1500
10 |  | Eel River Approach Channel | 1500 | Menauhant | 2000 | N | TOY Waiver Required | Dates TBD
11 |  | Green Pond Entrance Channel | 2000 | Acapesket Beach | 2000 | N | TOY Waiver Required | 2022-05-03 | 2022-06-02 | 2022-06-03 | 1038 | 1213
12 |  | Great Pond - Inside | 7500 | Four Seasons Beach | 2000 | N
13 |  | Great Pond Approach Channel | 500 | Four Seasons Beach | 2000 | N | TOY Waiver Required | 2022-05-03 | 2022-05-25 | 2022-05-26 | 441 | 610
| Dredge Sand Shifter |  |  | Dredge Sand Shifter |  |  | Dredge Sand Shifter |  |  | Dredge Sand Shifter
Project Order | TOWN | Dredge Site | Est. Vol. CY | Receiving | Pipeline | Booster | TOY's | Planned Start Date | Actual Start Date | Actual End Date | Pre-Dredge Estimated Volume | Post-Dredge Actual Volume
|  |  |  | Site | (LF) | (Y/N)
1 | Yarmouth | Englewood Channel (Lewis Bay) | 2000 | Colonial Acres Beach | 4000 | Y | CLOSE DTOY 1/14 | 2021-09-08
2 |  | Pine Island Cove Entrance (Lewis Bay) | 2000 | Colonial Acres Beach | 5000 | Y | CLOSE DTOY 1/14 | 2021-09-15
3 | Chatham | Mill Creek | 11000 | Forest & Pleasant Beach | 3500 | N | CLOSE DTOY 3/30 | 2021-09-13 | 2021-09-17 | 2021-10-09 | 11000 | 7410
4 | Chatham | Pleasant Bay/Strong Island Channel | 12000 | Scatteree Beach | 5000 | N | CLOSE DTOY 1/14 | 2021-09-27 | 2021-11-05 | 2021-12-01 | 12000 | 14720
5 | Yarmouth | Bass River Approach Channel | 4000 | Bass River Beach | 9000 | N | CLOSE DTOY 1/14 | 2021-10-20
6 |  | Bass River Entrance Channel | 500 | Bass River Beach |  | Y | CLOSE DTOY 1/14 | 2021-10-28
7 |  | Bass River (N/S of RT 28 Bridge) | 7000 | West Dennis Beach |  | Y | CLOSE DTOY 1/14 | 2021-11-05
8 | Bourne | Pocasset River | 4000 | Monument Beach/ Truck to Landfill | 7832 | N | CLOSE DTOY 1/14 | 2021-12-01 | 2021-12-18 | 2022-02-05 | 4000 | 3172
9 | Mashpee | Poppenessett Approach Ch | 9900 | Poppenessett Spit | 6600 | N | CLOSE DTOY 3/31 | 2021-12-20 | 2022-02-24 | 2022-03-21 | 5593 | 4860
10 | Chatham | Stage Harbor | 30000 | Cockle Cove & Hardings Beach | 11500 | Y | CLOSE DTOY 3/31 | 2021-01-15 | 2022-03-09 | 2022-03-26 | 40000 | 18346
11 | Harwich | Allen Harbor | 8000 | Grey Neck & Pleasant St. and Private Beaches | 3500 | N | OPEN DTOY 5/1 | 2021-05-02 | 2022-05-09 | 2022-05-27 | 10221 | 9686
12 |  | Wychmere Harbor | 3000 | Bank Street Beach | 3500 | N | OPEN DTOY 6/1 | 2021-06-01 | 2022-06-06 | 2022-06-09 | 3366 | 1191
Project Cancelled - Disposal Area No Longer Useable
Project Postponed - Additonal Permitting Required
Project Postponed - Additonal Permitting Required
Project Postponed - Only ~1,500 CY Available - Minimal Shoaling Present
Project Postponed - Minimal Shoaling Present
Project Postponed - Permit Not Available
Project Postponed - Comprehensive 10 Year Permit Pending Renewal
Project Postponed - Comprehensive 10 Year Permit Pending Renewal